## Outstanding Actions
Action Ref. | Meeting Title | Meeting Date | Category | Action | Allocated to: | Review Progress | Deadline | Status | Action Closed | Comments
1 | Leads Group | 2017-06-09 | Standard Products | Map procurement delivery framework against Standard Products | JR | 2017-07-21 |  | In Progress |  | insert relevant comments/progress update or updates from following meetings
11 | Leads Group | 2017-07-21 | General | United Utilities to circulate lessons learned from workshop with clients on DfMA tanks | JB | 2017-08-11 | 2017-11-15 | In Progress |  | 09/11/17 JB advised still not approved. Done by end Nov
12 | Leads Group | 2017-07-21 | Standard Products | Costain to follow up with client re. permission to share 25 standard products with Water Hub Group | SF | 2017-08-11 |  | In Progress |  | 08/09/17 - SF advised this is In progress
13 | Leads Group | 2017-07-21 | General | Bryden Wood to make book for Construction Projects Authority Available on their website. | JJ | 2017-08-11 |  | Not Started
14 | Leads Group | 2017-07-21 | General | Bryden Wood to seek permission from Highways to make book on infrastructure available on their website. | JJ | 2017-08-11 |  | Not Started
16 | Leads Group | 2017-07-21 | Roadmap: Business Case | Business Case: Examples of business cases to be sent to SF - these can be anonymised, if preferred. | ALL | 2017-09-02 |  | In Progress |  | 11/8/17 - Some business cases received but more examples would be welcome
19 | Leads Group | 2017-07-21 | Roadmap: Existing Products | Existing Products: Document the existing use cases of Standard Products.DM to lead. | DM | 2017-08-11 |  | In Progress |  | 08/09/17: DM to populate scoping document on Existing Products, considering definition of standard product as per the agreement at the client group meeting on 30/08. Group to send information to DM.
20 | Leads Group | 2017-07-21 | Roadmap | JR to work with Leads to agree scope and ToR for each project. | JR | 2017-08-11 |  | In Progress |  | 6/11/17: Most one pagers received. Yorkshire Water & Costain still outstanding - JR to follow up.
21 | Leads Group | 2017-07-21 | Events | Nomenca to arrange demonstration of “end to end” design, manufacture, install, commission. GS to work with JB and JR to scope out the visit. | GS | 2017-09-08 |  | In Progress |  | 11/08/17 GS liaising with JB to ensure this is not a repetition of previous visits. 08/09/17: GS advised that this may slip to May 2018
27 | Client Product Group | 2017-08-02 | Water Co. Standards | JR to follow up with CP on further guidance for Aimee Ladyman | JR | 2017-08-30 |  | In Progress |  | 06/11/17: JR advised that Mark Froggatt is following up with Aimee Ladyman
30 | Client Product Group | 2017-08-02 | Roadmap: Business Case | Circulate examples of business cases to the client group & send to LS to upload to website | MF | 2017-08-30 |  | Not Started |  | Originally allocated to CP. Re.allocated to MF 6/11/17,
34 | Client Product Group | 2017-08-02 | Standard Products | Figures for Yorkshire Water to be updated | SW | 2017-08-30 |  | Not Started
40 | Client Product Group | 2017-08-02 | Miscellaneous | Severn Trent to be given an overview of the BoS Website | JR/CD | 2017-08-30 |  | In Progress |  | 06/11/17: LS to arrange Skype call for week commencing 20/11/17
43 | Leads Group | 2017-08-11 | Roadmap | Volunteers requested from client/supplier/contractor/consultant areas for the various projects - Objective to produce a one page scoping document for each project.. Nomination/suggestions to JR. | ALL | 2017-09-02 |  | In Progress |  | JB has completed the first pass Comms Plan and accompanying one pager.
46 | Leads Group | 2017-08-11 | Roadmap: Existing Products | DM to liaise with GS to cover overlapping issues | DM | 2017-09-02 |  | Not Started
47 | Leads Group | 2017-08-11 | Roadmap: Existing Products | JR to add linkages to projects when one pagers are received | JR | 2017-09-02 |  | In Progress |  | 11/10/17:JR advised that he has received a 1-pager on existing products from DM.
48 | Leads Group | 2017-08-11 | Roadmap: Business Case | SF to write scopes | SF | 2017-09-02 | 2017-10-13 | In Progress |  | 08/09/17: SF to liaise with SW to write up a one pager on the business case both for joining Buildoffsite and for the use of standard products. First draft has been started but SF has not received any examples from other water hub members. 11/10/17: Action not progressed. SF/SW to speak.
54 | Leads Group | 2017-08-11 | Events | JR to update on Project 13 Event | JR | 2017-09-02 |  | Not Started
55 | Leads Group | 2017-08-11 | Meeting Admin | JR to invite MWH & Arup representative to participate in the group | JR | 2017-09-02 |  | In Progress |  | 06/11/17: MWH already invited. JR to invite Arup.
56 | Leads Group | 2017-08-11 | Miscellaneous | LS requested that the group think about case studies copy for the BoS website and Autumn Newsletter (which will be distributed at the OSCS.) | ALL | 2017-09-02 |  | Not Started |  | 06/11/17 - nothing received. Items still required for January newsletter. JB to share the high level Davyhulme case study as a starter (noted that a piece has already been done on this)
57 | Client Product Group | 2017-08-30 | Governance | JR to write guidance in constitution re. supply chain/confidentiality and use of percentages | JR | 2017-10-25 |  | In Progress |  | 25/10/17: JR advised this is on progress. He will send to LS for distribution, uploading to website.
60 | Client Product Group | 2017-08-30 | Miscellaneous | The photos on the BoS Water Hub area should be refreshed. All to send suitable photos to LS. | ALL | 2017-10-25 |  | In Progress |  | 25/10/17: LS advised no photos received. Action remains outstanding. All to find suitable images to send to LS. 09/11/17: Davyhulme photos received from UU
61 | Client Product Group | 2017-08-30 | Miscellaneous | JR/SW to send non confidential documents currently on Yorkshire Water SharePoint site to LS to upload to BoS website. | JR/SW | 2017-10-25 |  | In Progress |  | 13/10/17: Awaiting secure area t be set up on BoS Website. See Action no. 62
62 | Client Product Group | 2017-08-30 | Miscellaneous | LS to look feasibility of setting up a secure area of BoS website for water client group confidential documents. | LS | 2017-10-25 |  | In Progress |  | 25/10/17: Secure area of the BoS website has been commissioned. Web developers liaising with JB and SW to ensure compliance with Water company standards.
65 | Client Product Group | 2017-08-30 | Roadmap: Terminology | JR to check if terminology used by Offsite Management School BIM Special Interest Group aligns with BIM4Water terminology | JR | 2017-10-25 |  | In Progress |  | 25/10/17: Still outstanding. JR to speak to Sean McCarthy of Offsite Management School
66 | Client Product Group | 2017-08-30 | Offsite Management School | JB to follow up lean construction with Offsite Management School | JB | 2017-10-25 |  | In Progress |  | 25/10/17: JB presenting at OSMS seminar on Monday 29/10 in Coventry. JB working on this action - JR offered to assist. 09/11/17 In progress – missed opportunity at the last OMS Cov event to agree clear ties. JAB to arrange a call after running through with DK
68 | Client Product Group | 2017-08-30 | Offsite Management School | JB to Explore and clarify links between Offsite Management School and the BoS Water Hub and write a briefing/proposal. | JB | 2017-10-25 |  | In Progress |  | To be rolled up with Action 69.
69 | Client Product Group | 2017-08-30 | Offsite Management School | JB/DK to review offsite content from Offsite Management School website (what is relevant when you are building a product within the water industry) and produce review for Group. (To be used for gap analysis) | JB/DK | 2017-10-25 |  | Completed |  | 25/10/17: DK advised that he has started going through the OCS e-learning material to identify water specific items and will circulate what he has pulled together. There is disparity between learning materials - some are only one page and others lead to CPD accreditation. 22/11/17 - review circulated by DK.
70 | Client Product Group | 2017-08-30 | Offsite Management School | All to take some Offsite management School e-Learning modules to assess content | ALL | 2017-10-25 |  | In Progress |  | 25/10/17: Ongoing - some people have registered for modules.
71 | Client Product Group | 2017-08-30 | Roadmap: Efficiencies | JO to circulate the list of assumptions used to baseline Southern Water costs | JR | 2017-10-25 |  | In Progress |  | 25/10/17: LS has spoken to JO, who advised that he has sent the information to SW. JR to follow up. LS to follow up with JO & request details be sent to herself and JR
73 | Client Product Group | 2017-08-30 | Roadmap: Terminology | Consider the challenges to the definition of maturity levels, including the possible use of Technology Readiness Levers | SW | 2017-10-25 |  | In Progress |  | 25/10/17: JR to follow up with SW
74 | Client Product Group | 2017-08-30 | Roadmap: Terminology | Circulate diagram of products/product maturity | JR | 2017-10-25 |  | In Progress |  | 25/10/17: JR advised that this was drafted and he will circulate.
77 | Client Product Group | 2017-08-30 | Roadmap: Terminology | JR to liaise with CP re. definition of "reference designs" | JR | 2017-10-25 |  | In Progress |  | 25/10/17: JR has spoken with CP. JR to liaise with MF offline.
78 | Client Product Group | 2017-08-30 | Events | Look at setting up Director Level Conference in 2018, possibly as part of Project 13. | JR | 2017-10-25 |  | In Progress
79 | Client Product Group | 2017-08-30 | Miscellaneous | JR to list other offsite bodies and work that they are doing | JR | 2017-10-25 |  | Not Started |  | 25/10/17: action still outstanding
80 | Client Product Group | 2017-08-30 | Meeting Admin | Organise Quarterly meetings at Southern Water and Welsh Water | LS | 2017-10-25 |  | On Hold/To Be Advised |  | 25/10/17: LS to liaise with Water Co.s re. dates/venues for 2018.
81 | Leads Group | 2017-09-08 | Roadmap: Terminology | JR to circulate terminology agreed to date | JR | 2017-10-13 |  | In Progress |  | 11/10/17: JR advised that this has been done
83 | Leads Group | 2017-09-08 | Standard Products | JR to analyse standard products database and reduce the no. of standard products in line with the definition agreed by the client group on 30/08/17. | JR | 2017-10-13 |  | In Progress
84 | Leads Group | 2017-09-08 | Roadmap: Mapping | SW to map standard products/Supply Chain | SW | 2017-09-02 |  | In Progress
85 | Leads Group | 2017-09-08 | Events | JR to liaise with Steve Weston re. Possible visit to Ross-shire Engineering. Possibly March 2018 | JR | 2017-10-13 |  | In Progress |  | 08/09/17: JR met with Ross-Shire who are keen to get involved with BoS and happy consider an event being hosted at their site in Inverness.
86 | Leads Group | 2017-09-08 | Events | SF to look at possibility of visits to Wolston (Southampton) and Walton-On-Thames. | SF | 2017-10-13 |  | Not Started
87 | Leads Group | 2017-10-11 | Roadmap: Comms | JB to liaise with Nathalie Quinn at BoS regarding comms on the Water Hub Presentation at the OSCS | JB | 2017-11-10 |  | In Progress |  | 09/11/17: JAB in dialogue with NQ re comms plan and implementation. NQ due to call JAB with thoughts on next steps.
90 | Leads Group | 2017-10-11 | Roadmap: Comms | LS to liaise with NQ re. possible use of You Tube for videos from Water Hub Presentation at OSCS | LS | 2017-11-10 |  | In Progress
93 | Leads Group | 2017-10-11 | Information Management | LS to liaise with Client Group Members to agree anonymisation process for sharing sensitive information | LS | 2017-11-10 |  | Completed
94 | Leads Group | 2017-10-11 | Meeting Admin | JR to invite Jamie Mills from Xylem to client group meeting in Glasgow on 29/11/17 (Jamie is BIM4Water representative) | JR | 2017-11-10 |  | Completed
95 | Leads Group | 2017-10-11 | Events | JR to speak with Paul Rutter re. possible site visits | JR | 2017-11-10 |  | Not Started
96 | Leads Group | 2017-10-11 | Events | JB to speak with Moray Cotter re. possible site visits | JR | 2017-11-10 |  | Not Started
98 | Client Product Group | 2017-10-25 | Meeting Admin | JR to call IM prior to in-person meeting at Scottish Water on 20/11/17 | JR | 2017-11-20 | 2017-11-20 | Completed
99 | Client Product Group | 2017-10-25 | Miscellaneous | JR to call CD to update on water hub activities and progress to date | JR | 2017-11-20 |  | In Progress
100 | Client Product Group | 2017-10-25 | Roadmap | JR to draft and circulate a proposal for Client Group members to sponsor each roadmap project | JR | 2017-11-20 |  | Not Started
101 | Client Product Group | 2017-10-25 | Events | JR to liaise with MF re, possible site visits to filtration and sewage plants | JR/MF | 2017-11-29 |  | Not Started
102 | Client Product Group | 2017-10-25 | Miscellaneous | JR to call JM and demonstrate members' area of BoS Website | JR | 2017-11-20 |  | In Progress |  | 06/11/17: LS to arrange Skype call for week commencing 20/11/17
103 | Client Product Group | 2017-10-25 | Meeting Admin | Everyone to advise if they have specific agenda items for the meeting in Glasgow on 29/11/17 | All | 2017-11-20 |  | Completed
Note on D1: Category Column is optional. It provides a useful way to group and filter actions relating to a particular topic/area of work.
Note on E1: Insert details of action to be undertaken.
Note on F1: Insert name or initials of person/s to whom the action was allocated.
Note on I1: Categories available in drop down list: Not Started, In Progress, On Hold/To Be Advised, Completed
Note on J1: Insert date of meeting where actions were listed as "completed" or cleared.

## Completed Actions
Action Ref. | Meeting Title | Meeting Date | Category | Action | Allocated to: | Review Progress | Deadline | Status | Action Closed | Comments
2 | Leads Group | 2017-06-09 | Standard Products | Approach consultants to work together and have a standardised approach | ALL | 2017-07-21 |  | Completed |  | 21/07/17: JR advised that he has spoken to Arup and NWH and invited other members of the Leads Group to suggest consultants that could be approached.
3 | Leads Group | 2017-06-09 | Standard Products | Send Leads Group the Water Company Standards spreadsheet presented by Amy Ladyman at the Client Product Group Meeting on 24/05/17 | JR | n/a |  | Completed | 2017-07-21
4 | Leads Group | 2017-06-09 | Standard Products | Send Leads Group the common language agreed at the Client Product Group Meeting on 2405/17 | JR | n/a |  | Completed | 2017-07-21
5 | Leads Group | 2017-06-09 | Admin | Agree and distribute note from Client Product Group Meeting on 24/05/17 | JR | n/a |  | Completed | 2017-07-21
6 | Leads Group | 2017-06-09 | Standard Products | Common proposals document required for Standard Products | JR/SW | 2017-07-21 |  | Completed | 2017-09-08 | 21/07/17: JR to follow up with SW after monthly conference call. Rolled up into Action for everyone to complete one page scoping document.
7 | Leads Group | 2017-06-09 | Governance | Draft governance proposal to be sent to Leads Group | JR | 2017-06-14 |  | Completed | 2017-07-21 | Revised governance proposal circulated and upoaded on website.
8 | Leads Group | 2017-06-09 | Roadmap | Send thoughts on topics for common programmes to JR to add to road map | ALL | 2017-07-21 |  | Completed | 2017-09-08 | 21/07/17: discussed again on monthly conference call. 4 projects agreed (see minutes and further actions)
9 | Leads Group | 2017-06-09 | Events | Suggestions for future events to be suggested to JR | ALL | 2017-07-21 |  | Completed | 2017-09-08 | 21/07/17: discussed again on monthly conference call. Several events agreed (see minutes and further actions)
10 | Leads Group | 2017-06-09 | Governance | JB has invited Jack McCarey from SW Water to join the water hub. JR to follow up, | JR | 2017-07-21 |  | Completed | 2017-09-08
15 | Leads Group | 2017-07-21 | Roadmap: Business Case | Business Case: Set up a working group on the business case for offsite construction. SF with Support from SW. | SF | 2017-08-11 |  | Completed | 2017-09-08 | Woking group set up
17 | Leads Group | 2017-07-21 | Roadmap: Future Products | Future Product/Programme Alignment: project to compare the requirements of the future programme/projects against the Standard Products database to identify priorities and opportunities. GS to lead JB to assist. | GS | 2017-08-11 |  | Completed | 2017-09-08 | Project sheet scoped out - project in progress
18 | Leads Group | 2017-07-21 | Roadmap: Comms | Comms: Communications plan required to cover messages, channel, audience. JB to lead | JB | 2017-08-11 |  | Completed | 2017-09-08 | Project in progress
22 | Leads Group | 2017-07-21 | OSCS | JR to follow up on most favourable slots for Water Hub seminar at OSCS. | JR | 2017-08-11 |  | Completed | 2017-08-30
23 | Leads Group | 2017-07-21 | OSCS | All to promote OSCS to their networks | ALL | 2017-08-11 |  | Completed | 2017-09-08
24 | Leads Group | 2017-07-21 | OSCS | Scope what other events are being held in Excel at the same time as OSCS e.g. Flood Mitigation Show has been run at the same time in previous years. | LS | 2017-08-11 |  | Completed | 2017-09-08
25 | Leads Group | 2017-07-21 | Meeting Admin | DM to host 11th August Conference call at Davyhulme. Possibly combined with a site tour and work in the Roadmap and Communications Projects | DM | 2017-08-11 |  | Completed | 2017-08-11 | Cross reference with Action no. 42
26 | Client Product Group | 2017-08-02 | Front of Mind | Southern Water to circulate details of 9 efficiency levers to Client Product Group | PP | 2017-08-30 |  | Completed | 2017-08-10 | Levers email to group 10/08/17
28 | Client Product Group | 2017-08-02 | Water Co. Standards | Refresh of Project/Presentation to be added to agenda for 30th August | JR | 2017-08-30 |  | Completed | 2017-08-30
29 | Client Product Group | 2017-08-02 | Roadmap | Discussion around dealing with design only (not procurement) to be added to the agenda for 30th August. Also to be covered in TOR's for supply chain | JR | 2017-08-30 |  | Completed | 2017-08-30 | Added to agenda for 30/08/17
31 | Client Product Group | 2017-08-02 | Roadmap: Mapping | To be discussed further on 30th August | JR | 2017-08-30 |  | Completed | 2017-08-30
32 | Client Product Group | 2017-08-02 | Roadmap: Efficiencies | To be discussed further on 30th August | JR | 2017-08-30 |  | Completed | 2017-08-30
33 | Client Product Group | 2017-08-02 | Roadmap | Volunteers requested for the various projects. Nomination/suggestions to JR. | ALL | 2017-08-30 |  | Completed | 2017-09-09
35 | Client Product Group | 2017-08-02 | Terminology | Request to be sent to group members for terms which are a priority to define. | LS | 2017-08-30 | 2017-08-15 | Completed | 2017-08-30 | Email sent 22/08/17 - no responses received
36 | Client Product Group | 2017-08-02 | Miscellaneous | SW Water to be given an overview of the BoS Website | JR/JM | 2017-08-30 |  | Completed | 2017-08-30 | Done at meeting on 30/08/17
37 | Client Product Group | 2017-08-02 | Miscellaneous | Offline Discussion to be held re. links with Off Site Management School | JR/JB | 2017-08-30 |  | Completed | 2017-08-30 | Done at meeting on 30/08/17
38 | Client Product Group | 2017-08-02 | Meeting Admin | Hot topics/agenda items requested for meeting on 30th August. Feedback to JR/LS | ALL | 2017-08-22 | 2017-08-22 | Completed | 2017-08-30 | Email sent 22/08/17
39 | Client Product Group | 2017-08-02 | Meeting Admin | Future calls to be via Skype. JR/LS to liaise | JR/LS | 2017-08-30 |  | Completed |  | 11/08/17: raised again. JR to use his Skype account for future calls.
41 | Client Product Group | 2017-08-02 | Meeting Admin | BoS Membership & relationship with CIRIA to be added as an agenda item on 30th August | JR/LS | 2017-08-30 |  | Completed | 2017-08-30 | Added to agenda for 30/08/17
42 | Leads Group | 2017-08-11 | Meeting Admin | DM to host 8th September Conference call at Davyhulme. Possibly combined with a site tour and work in the Roadmap and Communications Projects | DM | 2017-09-01 |  | Completed
44 | Leads Group | 2017-08-11 | Roadmap: Comms | JB to send outline strawman to the group by 25/8/17 | JB | 2017-09-02 | 2017-08-25 | Completed |  | 08/09/17: Advised by JR that this had been completed
45 | Leads Group | 2017-08-11 | Roadmap: Existing Products | DM/JB to meet to discuss the list issued by JR prior to sending to the wider group. | DM | 2017-09-02 |  | Completed |  | 08/09/17: Advised by JR that this had been completed
49 | Leads Group | 2017-08-11 | Roadmap: Mapping | Southern Water note re catalogue of suppliers in water industry to be sent out to group. LS to liaise with PP | LS | 2017-09-02 |  | Completed |  | Cross reference with Action No. 84
50 | Leads Group | 2017-08-11 | Events | Aspiration for a director level conference in Spring/Summer 2018. To be added to comms plan | JB | 2017-09-02 |  | Completed |  | 30/08/17: Discussed at Client Group Quarterly Meeting. Cross reference with Action No. 78 11/10/17: JB advised that this event has been added to the Comms Plan.
51 | Leads Group | 2017-08-11 | OSCS | GS/DM to find a "volunteer" for the OSCS from the contractor/supplier side. | GS/DM | 2017-09-02 |  | Completed |  | 08/09/17: Advised by JR that this had been completed
52 | Leads Group | 2017-08-11 | OSCS | DM to approach LME & Lintott re. participation at the OSCS | DM | 2017-09-02 |  | Completed |  | 08/09/17: Advised by JR that this had been completed
53 | Leads Group | 2017-08-11 | OSCS | SW to approach Ross-shire re. participation at the OSCS | SW | 2017-09-02 |  | Completed |  | 08/09/17: JR has met with Ross-shire. They are participating in the OSCS presentation.
58 | Client Product Group | 2017-08-30 | Miscellaneous | LS to arrange a discussion with Tim Hall/JO to BoS in view of their CIRIA membership. | LS | 2017-09-30 |  | Completed |  | 25/10/17: LS advised that TH has spoken with JO
59 | Client Product Group | 2017-08-30 | Standard Products | Standard products spreadsheet to be removed from the BoS website. | LS | 2017-10-25 |  | Completed |  | Spreadsheet removed 31/08/17
63 | Client Product Group | 2017-08-30 | Miscellaneous | SW to look at 3rd party systems for sharing client confidential information | SW | 2017-10-25 |  | Completed |  | Action cancelled as action 62 now in progress.
64 | Client Product Group | 2017-08-30 | Water Co. Standards | JR to Liaise with Anglian Water (Chris Peel) to advise that water company standards work has been put on hold until a common terminology has been agreed, | JR | 2017-10-25 |  | Completed |  | 25/10/17: JR to discuss offline with MF
67 | Client Product Group | 2017-08-30 | Offsite Management School | JR to follow up the links between BoS Water & Offsite Management School | JR | 2017-10-25 |  | Completed |  | To be rolled up with Action 66.
72 | Client Product Group | 2017-08-30 | Roadmap: Terminology | BIM4Water to be invited to meeting on 29/11/17 | JR | 2017-10-25 |  | Completed |  | Jamie Mills from Xylem invited to the meeting in Glasgow on 29/11/17
75 | Client Product Group | 2017-08-30 | Roadmap: Terminology | Modify the definition of "standard product", as agreed | JR | 2017-10-25 |  | Completed
76 | Client Product Group | 2017-08-30 | Roadmap: Terminology | Modify the definition of "offsite", as agreed | JR | 2017-10-25 |  | Completed
82 | Leads Group | 2017-09-08 | Standard Products | All to provide comments to GS on standard products as he wants to freeze the scope by end of September | ALL | 2017-09-30 |  | Completed |  | 11/10/17: JR advised that GS has received 1 or 2 one-pagers and the scope of this project is now frozen
88 | Leads Group | 2017-10-11 | Roadmap: Comms | JR to send content from Water Hub Presentation at OSCS to NQ/LS with a copy to JB | JR | 2017-11-10 |  | Completed
89 | Leads Group | 2017-10-11 | Roadmap: Comms | LS to upload presentations from OSCS to website | LS | 2017-11-10 |  | Completed
91 | Leads Group | 2017-10-11 | Roadmap: Comms | LS to introduce NQ/JR/JB via email to enable the promotion of the Wayer Hub via social media, lunch and learn, webinars | LS | 2017-11-10 |  | Completed
92 | Leads Group | 2017-10-11 | Roadmap: Efficiencies | JR to ring CP at Anglian to discuss efficiencies workstream | LS | 2017-11-10 |  | Completed
97 | Leads Group | 2017-10-11 | Miscellaneous | LS to ask Lisa Norton to contact SWe at Ross-shire re. BoS Membership | LS | 2017-11-10 |  | Completed
Note on D1: Category Column is optional. It provides a useful way to group and filter actions relating to a particular topic/area of work.
Note on E1: Insert details of action to be undertaken.
Note on F1: Insert name or initials of person/s to whom the action was allocated.
Note on I1: Categories available in drop down list: Not Started, In Progress, On Hold/To Be Advised, Completed
Note on J1: Insert date of meeting where actions were listed as "completed" or cleared.

## Status (hidden)
Not Started
In Progress
Awaiting Response
On Hold
Completed